Carlos Area Fire Joint Powers Agreement (JPA) Meeting Minutes

Date: Wednesday, May 28, 2025
Start Time: 6:30 PM
Location: Carlos City Office

1. Call to Order

- Roll Call / Members Present

  - Ronna Berghoff, City of Carlos

  - Colten Steidl, Carlos Fire Department

  - Bill Krivanek, Carlos Township

  - Dwayne Waldorf, Carlos Township

  - Andy Miller, Belle River Township

  - James Young, City of Carlos

  - Adam Luckhart, Bolton and Menk

  - Jared Voge, Bolton and Menk

  - Attendance list

- Introduction of Board

2. Approval of Meeting Minutes

- Review and approval of minutes from May 12th, 2025

- Motion to approve minutes: Waldorf, second Krivanek – Passed

3. Reports

a. Treasurer’s Report

- No Treasurer’s Report

- Bolton and Menk bills totaling $93,251.00

  - Carlos Township - $69,938.68

  - City of Carlos - $13,987.74

  - Belle River - $9,325.16

- Outstanding bills

  - Bolton and Menk believe there are no more bills coming for current concept design, but if there are changes there will be expenses incurred.

  - These are not complete designs that can go to construction and bids, these are just concept designs. Around $160,000 more to get to construction for precast design.

4. Old Business

a. Project Discussion

- Bolton and Menk

  - Reviewed building and concept design options.

      - Talked about total dollar amount being nothing more $3 Million

      - But the cost is still up in the air due to June 3rd special meeting for Carlos Township.

    - Construction Quality Options

      - Good, Better, Best

    - In the Construction Admin Number from Bolton and Menk they discussed what is all covered. They want that number to include everything and will not need a check later on, when extra services are needed later on.

  - PEMB would be a $1.4 million savings from a precast

  - Current Sq Ft around 14,400

  - Specifics codes for a Fire Hall compared to other buildings – yes, example discussed the size of a water line. So it may not the be the structure integrity but other things that increase cost.

- Loan/Grant opportunities

  - USDA Loan – adds considerable time to the timeline and has to meet certain specifications; our research shows it would take 24-36 months to abide by their specifications.

  - FEMA BRIC Grant - adds considerable time to the timeline and has to meet certain specifications; our research shows it would take 24-36 months to abide by their specifications.

- Do we stay with Bolton and Menk –

  - All depends on June 3rd meeting discussion and what dollar amount feels sufficient.

  - Also depends on a more firm number we get from Bolton and Menk to discuss for next meeting.

- Next Steps:

  - Wait on June 3rd Special Meeting

5. New Business

a. Township & Community Feedback

- June 3rd Special Meeting will be held for Carlos Township

6. Miscellaneous

- Email sent to Dist. 206, to see if 5 year timeline can be extended. Waiting to hear back. Verbal feedback from Rick Stanstead (superintendent), they likely would approve this, but looking to get this in writing.

  - Will follow up with a phone call as we have no heard back from them.

8. Next Meeting Date and Time

- Confirm: June 9th, 2025 – 6:30 PM at Carlos City Hall

- Preliminary Agenda Items:

  - Discussion about reverse vote from Carlos Township

  - Continued Project Review, firm up dollar amount and solidify parameters.

  - Bolton and Menk to supply clearer dollar amounts.

9. Adjournment

- Motion to adjourn: Krivanek, second Waldorf – passed.

- Adjournment time recorded: 8:09 pm

- Notes completed by: Ronna Berghoff, Carlos Area Fire JPA, Secretary; City of Carlos, Mayor

JPA BOARD CONTACT INFORMATION:

Dwayne Waldorf - Dwayne.waldorf@icloud.com; (320) 219-0409

Andy Miller -  andysautorepair1@gmail.com; (320) 815-4142

Colten Steidl – cfd1251@gmail.com; (320) 766-0183

Bill Krivanek -  bkrivanek1961@gmail.com; (320) 815-9751

Ronna Berghoff – rberghoff@cityofcarlos.com; (320) 491-1892

James Young – jyoung@cityofcarlos.com; (320) 805-0294