Carlos Area Fire Joint Powers Agreement (JPA) Meeting Minutes

Date: Monday, August 3th, 2026
Start Time: 6:30 PM
Location: Carlos City Hall

1. Call to Order

- Roll Call / Members Present

  - Ronna Berghoff, City of Carlos

  - Jon Trenne, City of Carlos

  - Bill Krivanek, Carlos Township

  - Dwayne Waldorf, Carlos Township

  - Andy Miller, Belle River Township

  - Colton Steidl, Carlos Fire Department, Fire Chief

  - Dustin Tomoson, Ringdahl Architects

  - Jake Steidl, Carlos Fire Department

  - Mike Swensrud, Carlos Township Resident

  - Joe Cecko, Cecko Construction Co; CMAR of the Carlos Area Firehall project

  - Jason Murray, Drown and Associates

  - Mike Diebold, Carlos Township Resident

  - Mike Maudahl, Carlos Township Resident

  - Eric Thesing, Carlos Fire Department

- Introduction of Board and those in attendance.

2. Approval of Meeting Minutes

- Review and approval of minutes from July 27th, 2026

  - Motion to approve minutes: Waldorf, seconded Trenne  – Passed

3. Reports

a. Treasurer’s Report

- No Treasurers reports

4. Old Business

a. Project Discussion

- Review of bids that were submitted, Cecko Construction has opened, reviewed and organized bids

- Broken into many columns, base bid, with then 5 different Alternates.

- General discussion about bids that were received.

  - Work Scope #1 – Concrete, apparent low Tradesman Construction

  - Work Scope #2 – Metals, apparent low Boe Inc.

  - Work Scope #3 – Rough Carpentry, apparent low Tradesman Construction

  - Work Scope #4 – Finish Carpentry, apparent low Andrews Custom Carpentry

  - Work Scope #5 – Residential Casework, apparent low Schjenken – but not a complete bid, next would be Swedberg, waiting to hear back from Schjenken – going to go back and get bids specifically for p-lam.

  - Work Scope #6 – Insulation, apparent low M & M Insulation

  - Work Scope #7 – Doors, Frames and Hardware, apparent low Twin City Hardware

  - Work Scope #8 – Overhead Doors and Operators, apparent low Garage Door Store, but for a white door, red is a special order and it would add approximately $20,000 – discussed that white doors is fine.

  - Work Scope #9 – Gypsum System, apparent low Andrews Custom Carpentry

  - Work Scope #10 – Acoustical Ceilings, apparent low Wood Acoustics

  - Work Scope #11 – Flooring, apparent low Arnquist Flooring

  - Work Scope #12 – Painting, apparent low Henkemeyer Painting Inc.

  - Work Scope #13 – Misc. Specialties, apparent low Construction Supply

  - Work Scope #14 – Window Treatments, apparent low Cullens Carpet One on mid grade line

  - Work Scope #15 – Fire Suppression, apparent low Security Fire Sprinkler – but declined nitrogen generator

  - Work Scope #16 – Plumbing, apparent low Masters Plumbing

  - Work Scope #17 – HVAC, apparent low Ellingson Plumbing and Heating

  - Work Scope #18 – Electrical, apparent low Vinco Electric

  - Work Scope #19 – Earthwork and Site Utilities, apparent low Seph Construction

  - Work Scope #20 – Asphalt Paving – no direct bidding all in earth work

  - Work Scope #21 – Landscaping, apparent low Alex Irrigation

  - 5% owner contingency – is bonded for right away and if it is not used it gets applied to the new balance going forward.

- Base bid amount= $2,122,358.41

  - alt 1 = $96,400 = generator – Board voted No to alternate 1

  - alt 2 = $145,653.14 = asphalt - Board voted no to alternate 2

  - alt 3 = $23,440.00 = recycled bituminous - Board voted no to alternate 3

  - alt 4 = $8,720.10 = mini split – Board voted no to alternate 4

  - alt 5 = ($19,705) = spring start - Board voted no to alternate 5

- Soft cost = $217,102.95

- From Notes of CMAR, Joe Cecko:

  - None of the alternates 1-5 were accepted.

  - Alternate #3 was updated to reflect the accurate cost of $23,727.53 if accepted and Tradesmen became the low Earthwork bidder.

  - I will pursue additional bids for p-lam casework for cost savings. Currently showing low complete oak casework proposal.

  - Add of $19,542 for custom OH door color red was not accepted.

  - Changed window treatments to Cullen’s mid-range grade blinds of $2,664.86.

  - Add of $13,950 for fire protection dry system nitrogen generator was not accepted.

  - Add of $15,945 for lawn irrigation was not accepted. Owner will provide watering and maintenance.

  - A CMAR contingency is not included. Owner assumes risk in bid pricing being honored at time of contract execution.

  - Owner Soft Costs

  - Added legal fees of $20,000.

  - Revised FF & E budget from $128,00 to $66,000.

  - Jason, please provide debt service fees to be added to Total Project Cost. For presentation purposes to the public, I feel it would be good to keep total project cost under $2.7M if possible while still allowing for appropriate financial cushion.

- Jason Murray – capitalized interest included, used a number of $2,475,000, but with capitalized interest around debt impact number would be $2,700,000. Term of 20 years – look at attached.

- Carlos township passed the resolution to hold special meeting on Aug 6th to review the bids and formulate the question to be placed on the November ballot.

- Dan Burns with Fryberger Law will help write and finalize the question that will be placed on the ballot for November for Carlos Township.

5. New Business

a. Building Committee

- Committee Members:

  - Mike Swendsrud – Present – added comments throughout the review of bids

  - Lawerence Keenan – Not Present

  - Fire Department Members

    - 2-3 Fireman

e. Getting information out for special election vote in November:

- Public information meeting (monthly or just Mid-October)

- Carlos Township meeting will be sending out a newsletter and explaining the project (Sept)

- Schedule meeting with a one on one interview with Echo Press or letter to Editor

- Open line

6. Miscellaneous

a. Discussion on how to inform our residents about the project to make a fully educated decision. – discussion just above.

7. Next Meeting Date and Time

- Confirm: August 10th, 2026 – 6:30 PM at Carlos City Hall

- Preliminary Agenda Items:

  - How to inform the public about the project

8. Adjournment

- Motion to adjourn: Waldorf, second Berghoff – passed.

- Adjournment time recorded: 9:02 pm

- Notes completed by: Ronna Berghoff, Carlos Area Fire JPA, Secretary; City of Carlos, Mayor

JPA BOARD CONTACT INFORMATION:

Dwayne Waldorf - Dwayne.waldorf@icloud.com; (320) 219-0409

Andy Miller -  andysautorepair1@gmail.com; (320) 815-4142

Colten Steidl – cfd1251@gmail.com; (320) 766-0183

Bill Krivanek -  bkrivanek1961@gmail.com; (320) 815-9751

Ronna Berghoff – rberghoff@cityofcarlos.com; (320) 491-1892

Jon Trenne – jtrenne@cityofcarlos.com; (320) 491-2126